## Burndown Chart
Sprint 3 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20
|  | Day 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Find/discribe related use cases (Francisco) | Day 0: 2; 3: 1; 4: 1
2 | Find/discribe related use cases (Iago) | Day 0: 2; 2: 1; 3: 1
3 | Find/discribe related use cases (James) | Day 0: 2; 2: 1; 3: 1
4 | Find/discribe related use cases (Joaoa) | Day 0: 2; 3: 2
5 | Find/discribe related use cases (Ricardo) | Day 0: 2; 3: 1; 4: 1
6 | Develop an use case sub-diagram (Francisco) | bar: Day 0; 4
7 | Develop an use case sub-diagram (Iago) | bar: Day 0; 3
8 | Develop an use case sub-diagram (James) | bar: Day 0; 3
9 | Develop an use case sub-diagram (Joao) | bar: Day 0; 4
10 | Develop an use case sub-diagram (Ricardo) | bar: Day 0; 4
Completed Effort |  | 0 | 0 | 2 | 8 | 5 | 0 | 0 | 0
Remaining Effort |  | 15 | 15 | 13 | 5 | 0 | 0 | 0 | 0
Ideal Burndown |  | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0