## Burndown Chart
Sprint 2 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-11 | 2022-11-13
|  | Day 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Sugerir 2 Features (Francisco) | bar: Day 0 to 1
2 | Sugerir 2 Features (Iago) | bar: Day 0 to 1
3 | Sugerir 2 Features (James) | bar: Day 0 to 1
4 | Sugerir 2 Features (Joao) | bar: Day 0 to 1
5 | Sugerir 2 Features (Ricardo) | bar: Day 0 to 1
6 | Criar User Story Primeira Feature | bar: Day 0; 2
7 | Criar User Story Segunda Feature | bar: Day 0; 2
8 | Descrever Totalmente Primeita Feature | Day 0: 2; 3: 1; 4: 1
9 | Descrever Totalmente Segunda Feature | Day 0: 2; 3: 1; 4: 1
Completed Effort |  | 0 | 5 | 2 | 2 | 2 | 0 | 0 | 0
Remaining Effort |  | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Ideal Burndown |  | 11 | 9.4286 | 7.8571 | 6.2857 | 4.7143 | 3.1429 | 1.5714 | 0