## Burndown Chart
Sprint 4 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27
|  | Day 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Debug the code to know how it works | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0
2 | Find and correct possible bugs (It had one) | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
3 | See how to implement feature 1 (Ricardo) and 2 (James,Iago,Francisco,Joao) | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0
4 | Create a java program to encapsulate tasks so James can use in the ganttproject | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Completed Effort |  | 0 | 1 | 1 | 2 | 1 | 1 | 0.5 | 0.5
Remaining Effort |  | 7 | 6 | 5 | 3 | 2 | 1 | 0.5 | 0
Ideal Burndown |  | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0